{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Gantt"],"read":"whole","date_system":"1900"}

{"sheet":"Gantt","index":0,"n_rows":41,"n_cols":245,"rows_kept":41}
[null,"Interference Injection Tool"]
[null,"Team: 1"]
[null,"Project start date","2025-11-05"]
[null,"Project end date","2026-06-12",{"$nulls":4},{"$f":"TEXT(H6,\"mmm\")","v":"Nov"},{"$nulls":25},{"$f":"TEXT(AH6,\"mmm\")","v":"Dec"},{"$nulls":30},{"$f":"TEXT(BM6,\"mmm\")","v":"Jan"},{"$nulls":30},{"$f":"TEXT(CR6,\"mmm\")","v":"Feb"},{"$nulls":27},{"$f":"TEXT(DT6,\"mmm\")","v":"Mar"},{"$nulls":30},{"$f":"TEXT(EY6,\"mmm\")","v":"Apr"},{"$nulls":29},{"$f":"TEXT(GC6,\"mmm\")","v":"May"},{"$nulls":30},{"$f":"TEXT(HH6,\"mmm\")","v":"Jun"}]
[{"$nulls":7},{"$f":"_xlfn.ISOWEEKNUM(H6)","v":45},{"$nulls":4},{"$f":"_xlfn.ISOWEEKNUM(M6)","v":46},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(T6)","v":47},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(AA6)","v":48},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(AH6)","v":49},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(AO6)","v":50},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(AV6)","v":51},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(BC6)","v":52},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(BJ6)","v":1},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(BQ6)","v":2},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(BX6)","v":3},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(CE6)","v":4},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(CL6)","v":5},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(CS6)","v":6},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(CZ6)","v":7},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(DG6)","v":8},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(DN6)","v":9},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(DU6)","v":10},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(EB6)","v":11},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(EI6)","v":12},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(EP6)","v":13},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(EW6)","v":14},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(FD6)","v":15},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(FK6)","v":16},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(FR6)","v":17},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(FY6)","v":18},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(GF6)","v":19},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(GM6)","v":20},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(GT6)","v":21},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(HA6)","v":22},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(HH6)","v":23},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(HO6)","v":24},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(HV6)","v":25},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(IC6)","v":26},{"$nulls":6},{"$f":"_xlfn.ISOWEEKNUM(IJ6)","v":27}]
[{"$nulls":7},{"$f":"C3","v":"2025-11-05"},{"$f":"H6+1","v":"2025-11-06"},{"$f":"I6+1","v":"2025-11-07"},{"$f":"J6+1","v":"2025-11-08"},"2025-11-09","2025-11-10","2025-11-11","2025-11-12","2025-11-13","2025-11-14","2025-11-15","2025-11-16","2025-11-17","2025-11-18","2025-11-19","2025-11-20","2025-11-21","2025-11-22","2025-11-23","2025-11-24","2025-11-25","2025-11-26","2025-11-27","2025-11-28","2025-11-29","2025-11-30","2025-12-01","2025-12-02","2025-12-03","2025-12-04","2025-12-05","2025-12-06","2025-12-07","2025-12-08","2025-12-09","2025-12-10","2025-12-11","2025-12-12","2025-12-13","2025-12-14","2025-12-15","2025-12-16","2025-12-17","2025-12-18","2025-12-19","2025-12-20","2025-12-21",{"$f":"BB6+1","v":"2025-12-22"},{"$f":"BC6+1","v":"2025-12-23"},{"$f":"BD6+1","v":"2025-12-24"},{"$f":"BE6+1","v":"2025-12-25"},{"$f":"BF6+1","v":"2025-12-26"},{"$f":"BG6+1","v":"2025-12-27"},{"$f":"BH6+1","v":"2025-12-28"},{"$f":"BI6+1","v":"2025-12-29"},{"$f":"BJ6+1","v":"2025-12-30"},{"$f":"BK6+1","v":"2025-12-31"},{"$f":"BL6+1","v":"2026-01-01"},{"$f":"BM6+1","v":"2026-01-02"},{"$f":"BN6+1","v":"2026-01-03"},{"$f":"BO6+1","v":"2026-01-04"},{"$f":"BP6+1","v":"2026-01-05"},{"$f":"BQ6+1","v":"2026-01-06"},{"$f":"BR6+1","v":"2026-01-07"},{"$f":"BS6+1","v":"2026-01-08"},{"$f":"BT6+1","v":"2026-01-09"},{"$f":"BU6+1","v":"2026-01-10"},{"$f":"BV6+1","v":"2026-01-11"},{"$f":"BW6+1","v":"2026-01-12"},{"$f":"BX6+1","v":"2026-01-13"},{"$f":"BY6+1","v":"2026-01-14"},{"$f":"BZ6+1","v":"2026-01-15"},{"$f":"CA6+1","v":"2026-01-16"},{"$f":"CB6+1","v":"2026-01-17"},{"$f":"CC6+1","v":"2026-01-18"},{"$f":"CD6+1","v":"2026-01-19"},{"$f":"CE6+1","v":"2026-01-20"},{"$f":"CF6+1","v":"2026-01-21"},{"$f":"CG6+1","v":"2026-01-22"},{"$f":"CH6+1","v":"2026-01-23"},{"$f":"CI6+1","v":"2026-01-24"},{"$f":"CJ6+1","v":"2026-01-25"},{"$f":"CK6+1","v":"2026-01-26"},{"$f":"CL6+1","v":"2026-01-27"},{"$f":"CM6+1","v":"2026-01-28"},{"$f":"CN6+1","v":"2026-01-29"},{"$f":"CO6+1","v":"2026-01-30"},{"$f":"CP6+1","v":"2026-01-31"},{"$f":"CQ6+1","v":"2026-02-01"},{"$f":"CR6+1","v":"2026-02-02"},{"$f":"CS6+1","v":"2026-02-03"},{"$f":"CT6+1","v":"2026-02-04"},{"$f":"CU6+1","v":"2026-02-05"},{"$f":"CV6+1","v":"2026-02-06"},{"$f":"CW6+1","v":"2026-02-07"},{"$f":"CX6+1","v":"2026-02-08"},{"$f":"CY6+1","v":"2026-02-09"},{"$f":"CZ6+1","v":"2026-02-10"},{"$f":"DA6+1","v":"2026-02-11"},{"$f":"DB6+1","v":"2026-02-12"},{"$f":"DC6+1","v":"2026-02-13"},{"$f":"DD6+1","v":"2026-02-14"},{"$f":"DE6+1","v":"2026-02-15"},{"$f":"DF6+1","v":"2026-02-16"},{"$f":"DG6+1","v":"2026-02-17"},{"$f":"DH6+1","v":"2026-02-18"},{"$f":"DI6+1","v":"2026-02-19"},{"$f":"DJ6+1","v":"2026-02-20"},{"$f":"DK6+1","v":"2026-02-21"},{"$f":"DL6+1","v":"2026-02-22"},{"$f":"DM6+1","v":"2026-02-23"},{"$f":"DN6+1","v":"2026-02-24"},{"$f":"DO6+1","v":"2026-02-25"},{"$f":"DP6+1","v":"2026-02-26"},{"$f":"DQ6+1","v":"2026-02-27"},{"$f":"DR6+1","v":"2026-02-28"},{"$f":"DS6+1","v":"2026-03-01"},{"$f":"DT6+1","v":"2026-03-02"},{"$f":"DU6+1","v":"2026-03-03"},{"$f":"DV6+1","v":"2026-03-04"},{"$f":"DW6+1","v":"2026-03-05"},{"$f":"DX6+1","v":"2026-03-06"},{"$f":"DY6+1","v":"2026-03-07"},{"$f":"DZ6+1","v":"2026-03-08"},{"$f":"EA6+1","v":"2026-03-09"},{"$f":"EB6+1","v":"2026-03-10"},{"$f":"EC6+1","v":"2026-03-11"},{"$f":"ED6+1","v":"2026-03-12"},{"$f":"EE6+1","v":"2026-03-13"},{"$f":"EF6+1","v":"2026-03-14"},{"$f":"EG6+1","v":"2026-03-15"},{"$f":"EH6+1","v":"2026-03-16"},{"$f":"EI6+1","v":"2026-03-17"},{"$f":"EJ6+1","v":"2026-03-18"},{"$f":"EK6+1","v":"2026-03-19"},{"$f":"EL6+1","v":"2026-03-20"},{"$f":"EM6+1","v":"2026-03-21"},{"$f":"EN6+1","v":"2026-03-22"},{"$f":"EO6+1","v":"2026-03-23"},{"$f":"EP6+1","v":"2026-03-24"},{"$f":"EQ6+1","v":"2026-03-25"},{"$f":"ER6+1","v":"2026-03-26"},{"$f":"ES6+1","v":"2026-03-27"},{"$f":"ET6+1","v":"2026-03-28"},{"$f":"EU6+1","v":"2026-03-29"},{"$f":"EV6+1","v":"2026-03-30"},{"$f":"EW6+1","v":"2026-03-31"},{"$f":"EX6+1","v":"2026-04-01"},{"$f":"EY6+1","v":"2026-04-02"},{"$f":"EZ6+1","v":"2026-04-03"},{"$f":"FA6+1","v":"2026-04-04"},{"$f":"FB6+1","v":"2026-04-05"},{"$f":"FC6+1","v":"2026-04-06"},{"$f":"FD6+1","v":"2026-04-07"},{"$f":"FE6+1","v":"2026-04-08"},{"$f":"FF6+1","v":"2026-04-09"},{"$f":"FG6+1","v":"2026-04-10"},{"$f":"FH6+1","v":"2026-04-11"},{"$f":"FI6+1","v":"2026-04-12"},{"$f":"FJ6+1","v":"2026-04-13"},{"$f":"FK6+1","v":"2026-04-14"},{"$f":"FL6+1","v":"2026-04-15"},{"$f":"FM6+1","v":"2026-04-16"},{"$f":"FN6+1","v":"2026-04-17"},{"$f":"FO6+1","v":"2026-04-18"},{"$f":"FP6+1","v":"2026-04-19"},{"$f":"FQ6+1","v":"2026-04-20"},{"$f":"FR6+1","v":"2026-04-21"},{"$f":"FS6+1","v":"2026-04-22"},{"$f":"FT6+1","v":"2026-04-23"},{"$f":"FU6+1","v":"2026-04-24"},{"$f":"FV6+1","v":"2026-04-25"},{"$f":"FW6+1","v":"2026-04-26"},{"$f":"FX6+1","v":"2026-04-27"},{"$f":"FY6+1","v":"2026-04-28"},{"$f":"FZ6+1","v":"2026-04-29"},{"$f":"GA6+1","v":"2026-04-30"},{"$f":"GB6+1","v":"2026-05-01"},{"$f":"GC6+1","v":"2026-05-02"},{"$f":"GD6+1","v":"2026-05-03"},{"$f":"GE6+1","v":"2026-05-04"},{"$f":"GF6+1","v":"2026-05-05"},{"$f":"GG6+1","v":"2026-05-06"},{"$f":"GH6+1","v":"2026-05-07"},{"$f":"GI6+1","v":"2026-05-08"},{"$f":"GJ6+1","v":"2026-05-09"},{"$f":"GK6+1","v":"2026-05-10"},{"$f":"GL6+1","v":"2026-05-11"},{"$f":"GM6+1","v":"2026-05-12"},{"$f":"GN6+1","v":"2026-05-13"},{"$f":"GO6+1","v":"2026-05-14"},{"$f":"GP6+1","v":"2026-05-15"},{"$f":"GQ6+1","v":"2026-05-16"},{"$f":"GR6+1","v":"2026-05-17"},{"$f":"GS6+1","v":"2026-05-18"},{"$f":"GT6+1","v":"2026-05-19"},{"$f":"GU6+1","v":"2026-05-20"},{"$f":"GV6+1","v":"2026-05-21"},{"$f":"GW6+1","v":"2026-05-22"},{"$f":"GX6+1","v":"2026-05-23"},{"$f":"GY6+1","v":"2026-05-24"},{"$f":"GZ6+1","v":"2026-05-25"},{"$f":"HA6+1","v":"2026-05-26"},{"$f":"HB6+1","v":"2026-05-27"},{"$f":"HC6+1","v":"2026-05-28"},{"$f":"HD6+1","v":"2026-05-29"},{"$f":"HE6+1","v":"2026-05-30"},{"$f":"HF6+1","v":"2026-05-31"},{"$f":"HG6+1","v":"2026-06-01"},{"$f":"HH6+1","v":"2026-06-02"},{"$f":"HI6+1","v":"2026-06-03"},{"$f":"HJ6+1","v":"2026-06-04"},{"$f":"HK6+1","v":"2026-06-05"},{"$f":"HL6+1","v":"2026-06-06"},{"$f":"HM6+1","v":"2026-06-07"},{"$f":"HN6+1","v":"2026-06-08"},{"$f":"HO6+1","v":"2026-06-09"},{"$f":"HP6+1","v":"2026-06-10"},{"$f":"HQ6+1","v":"2026-06-11"},{"$f":"HR6+1","v":"2026-06-12"},{"$f":"HS6+1","v":"2026-06-13"},{"$f":"HT6+1","v":"2026-06-14"},{"$f":"HU6+1","v":"2026-06-15"},{"$f":"HV6+1","v":"2026-06-16"},{"$f":"HW6+1","v":"2026-06-17"},{"$f":"HX6+1","v":"2026-06-18"},{"$f":"HY6+1","v":"2026-06-19"},{"$f":"HZ6+1","v":"2026-06-20"},{"$f":"IA6+1","v":"2026-06-21"},{"$f":"IB6+1","v":"2026-06-22"},{"$f":"IC6+1","v":"2026-06-23"},{"$f":"ID6+1","v":"2026-06-24"},{"$f":"IE6+1","v":"2026-06-25"},{"$f":"IF6+1","v":"2026-06-26"},{"$f":"IG6+1","v":"2026-06-27"},{"$f":"IH6+1","v":"2026-06-28"},{"$f":"II6+1","v":"2026-06-29"},{"$f":"IJ6+1","v":"2026-06-30"}]
[{"$nulls":7},{"$f":"TEXT(H6,\"d\")","v":"5"},{"$f":"TEXT(I6,\"d\")","v":"6"},{"$f":"TEXT(J6,\"d\")","v":"7"},{"$f":"TEXT(K6,\"d\")","v":"8"},"9","10","11","12","13","14","15","16","17","18","19","20","21","22","23","24","25","26","27","28","29","30","1","2","3","4","5","6","7","8","9","10","11","12","13","14","15","16","17","18","19","20","21",{"$f":"TEXT(BC6,\"d\")","v":"22"},"23","24","25","26","27","28","29","30","31","1","2","3","4","5","6","7","8","9","10","11","12","13","14","15","16","17","18",{"$f":"TEXT(CE6,\"d\")","v":"19"},"20","21","22","23","24","25","26","27","28","29","30","31","1","2","3","4","5","6","7","8","9","10","11","12","13","14","15","16","17","18","19","20","21","22","23","24","25","26","27","28","1","2","3","4","5","6","7","8","9","10","11","12","13","14","15","16","17","18","19","20","21","22","23",{"$f":"TEXT(EQ6,\"d\")","v":"24"},"25","26","27","28","29","30","31","1","2","3","4","5","6","7","8","9","10","11","12","13","14","15","16","17","18","19","20","21","22","23","24","25","26","27","28","29","30","1","2","3","4","5","6","7","8","9","10","11","12","13","14","15","16","17","18","19","20","21","22","23","24","25","26",{"$f":"TEXT(HC6,\"d\")","v":"27"},"28","29","30","31","1","2","3","4","5","6","7","8","9","10","11","12","13","14","15","16","17","18","19","20","21","22","23","24","25","26","27","28","29","30"]
[]
[null,"Task","Assigned to","Progress","Start","End",null,{"$f":"TEXT(H6,\"ddd\")","v":"Wed"},{"$f":"TEXT(I6,\"ddd\")","v":"Thu"},{"$f":"TEXT(J6,\"ddd\")","v":"Fri"},{"$f":"TEXT(K6,\"ddd\")","v":"Sat"},"Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun",{"$f":"TEXT(BC6,\"ddd\")","v":"Mon"},"Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun",{"$f":"TEXT(CE6,\"ddd\")","v":"Mon"},"Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon",{"$f":"TEXT(EQ6,\"ddd\")","v":"Tue"},"Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue",{"$f":"TEXT(HC6,\"ddd\")","v":"Wed"},"Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue","Wed","Thu","Fri","Sat","Sun","Mon","Tue"]
[null,"Requirement analysis",null,null,{"$f":"MIN(E11)","v":"2025-11-05"},{"$f":"MAX(F11)","v":"2025-11-19"}]
[null,"Clarify requirements","Business analyst",100,{"$f":"C3","v":"2025-11-05"},{"$f":"E11+14","v":"2025-11-19"}]
[null,"Design",null,null,{"$f":"MIN(E13:E15)","v":"2025-11-12"},{"$f":"MAX(F13:F15)","v":"2025-11-24"}]
[null,"Decide on technologies and frameworks","Solution Architect",50,"2025-11-12",{"$f":"E13+1","v":"2025-11-13"}]
[null,"Create UI/UX design","UI/UX designer",0,"2025-11-12",{"$f":"E14+7","v":"2025-11-19"}]
["M","Create technical specification","Solution Architect",0,"2025-11-17",{"$f":"E15+7","v":"2025-11-24"}]
[null,"Development",null,null,{"$f":"MIN(E17:E30)","v":0},{"$f":"MAX(F17:F30)","v":0}]
[null,"Develop Add interference tab"]
[null,"Develop import clean signal","Developer",0]
[null,"Visualize clean signal","Developer",0]
[null,"Develop import interference","Developer",0]
[null,"Visualize interference","Developer",0]
[null,"Develop interference parameter adjustments","Developer",0]
[null,"Visualize adjustments","Developer",0]
[null,"Develop interference injection","Developer",0]
[null,"Develop signal processing","Developer",0]
[null,"Develop export functionality","Developer",0]
[null,"Develop analyze export tab"]
[null,"Visulize interfered signal","Developer",0]
[null,"Develop statistical analysis","Developer",0]
[null,"Develop export analysis","Developer",0]
[null,"Testing",null,null,{"$f":"MIN(E32:E34)","v":0},{"$f":"MAX(F32:F34)","v":0}]
[null,"Prepare test cases","Tester",0]
[null,"Perform tests","Tester",0]
[null,"Correct bugs","Developer",0]
[null,"Deployment",null,null,{"$f":"MIN(E36:E38)","v":0},{"$f":"MAX(F36:F38)","v":0}]
[null,"Deploy application","Solution architect / Developer",0]
[null,"Update technical specification","Solution Architect",0]
[null,"Write user manual","Business analyst",0]
[null,"Project presentation",null,null,{"$f":"MIN(E40:E41)","v":"2026-06-01"},{"$f":"MAX(F40:F41)","v":"2026-06-12"}]
[null,"Prepare final presentation","Team",0,"2026-06-01",{"$f":"E40+10","v":"2026-06-11"}]
[null,"Present the project","Team",0,"2026-06-12",{"$f":"C4","v":"2026-06-12"}]